## Summary
Release Notes — sprint-12
BUILD INFORMATION
Sprint | sprint-12
Sprint Dates | 2026-06-09 → 2026-06-20
Build Date | 2026-06-20
Built By | john.smith
ELM Sprint | https://elm.company.com/ccm/web/projects/MyProject#action=com.ibm.team.apt.viewPage&id=sprint-12
ENVIRONMENT STATUS
Environment | Status | Deployed By | Date | Notes
SIT | deployed | john.smith | 2026-06-20 14:30
UAT | pending | — | — | UAT currently running sprint-11
Generated by generate-report.js on 2026-06-12 03:11

## Teams
Team | Source | Included | Branch / Folder | Version / SHA | ELM Work Items | Summary | Defer Reason
Conversion | SHAREPOINT | YES | https://company.sharepoint.com/sites/ETL/Shared Documents/sprint-12 | v1.3 | ELM-1201 ELM-1202 ELM-1208 | Customer address mapping null-safe account load
Interfaces | GIT | YES | sprint/sprint-12 | b2c3d4e5 | ELM-1210 ELM-1215 | REST adapter v2 endpoint updates retry logic
Workflow Config | GIT | NO | sprint/sprint-12 |  | ELM-1220 ELM-1221 |  | ELM-1220 blocked pending sign-off from business deferred to sprint-13
Functional Product Config | GIT | YES | sprint/sprint-12 | c3d4e5f6 | ELM-1230 ELM-1231 | Product configuration tables updated for region codes

## COTS
COTS Product Details
Product | Acme ETL Platform
Version | 2.4.0
Previous Version | 2.3.8
Hotfixes | HF-2024-011 HF-2024-012
Included | Yes
Notes | Upgrade from 2.3.8 schema change in audit_log table
Release Notes File | cots-sprint-12.md