## Build Info
Field | Value
release | sprint-12
sprint_dates | 2026-06-09 → 2026-06-20
build_date | 2026-06-20
built_by | john.smith
elm_sprint_url | https://elm.company.com/ccm/web/projects/MyProject#action=com.ibm.team.apt.viewPage&id=sprint-12

## Teams
team_key | team_name | source_control | repo_or_sharepoint_url | branch | commit_or_artifact_version | included | elm_work_items | summary | notes | depends_on | reason_if_deferred
conversion | Conversion Team | sharepoint | https://company.sharepoint.com/sites/ETL/Shared Documents/sprint-12 | N/A | v1.3 | TRUE | ELM-1201 ELM-1202 ELM-1208 | Customer address mapping null-safe account load
interfaces | Interfaces Team | git | satishreddy13/repo-interfaces | sprint/sprint-12 | b2c3d4e5 | TRUE | ELM-1210 ELM-1215 | REST adapter v2 endpoint updates retry logic |  | func_config
workflow_config | Workflow Config Team | git | satishreddy13/repo-workflow-config | sprint/sprint-12 |  | FALSE | ELM-1220 ELM-1221 |  |  |  | ELM-1220 blocked pending sign-off from business deferred to sprint-13
func_config | Functional Product Config | git | satishreddy13/repo-func-config | sprint/sprint-12 | c3d4e5f6 | TRUE | ELM-1230 ELM-1231 | Product configuration tables updated for region codes

## COTS
Field | Value
product | Acme ETL Platform
version | 2.4.0
previous_version | 2.3.8
hotfixes_included | HF-2024-011 HF-2024-012
included | TRUE
notes | Upgrade from 2.3.8 schema change in audit_log table
release_notes_file | cots-sprint-12.md

## Environments
environment | status | deployed_by | deployed_date | passed_date | notes
sit | deployed | john.smith | 2026-06-20 14:30
uat | pending |  |  |  | UAT currently running sprint-11